## Chatt Sch
Activity ID | Name | Start Day | Dur | Adjust
#1001 | _Pre_Construction_Day_01 | 1 | 1 | 0
00020 | SALES - Home Def Entered | 1 | 1 | -9
20111 | DIV-PlanFilesSharePoint | 1 | 1 | -9
20119 | CAD-CreateLotSpecPkg | 1 | 1 | -7
20120 | CAD - Start Draw Process | 1 | 1 | -6
20150 | CAD - Plans Complete | 1 | 1 | -2

## Sheet4
Row Labels | Current | NEW | Grand Total
#1001 | 1 | 1 | 2
#1002 | 1 | 1 | 2
#1003 | 1 | 1 | 2
#1004 | 1 | 1 | 2
#1zbb | 1 | 1 | 2
#2s01 | 1 | 1 | 2
#2s02 | 1 | 1 | 2
#2s03 | 1 | 1 | 2
#2s04 | 1 | 1 | 2
#2s05 | 1 | 1 | 2
#2s06 | 1 | 1 | 2
#2s07 | 1 | 1 | 2
#2s08 | 1 |  | 1
#2s09 | 1 |  | 1
#2s10 | 1 |  | 1
#2zbb | 1 | 1 | 2
#3001 | 1 | 1 | 2
#3002 | 1 | 1 | 2
#3003 | 1 | 1 | 2
#3004 | 1 | 1 | 2
#3005 | 1 | 1 | 2
#3006 | 1 | 1 | 2
#3007 | 1 | 1 | 2
#3008 | 1 | 1 | 2
#3009 | 1 | 1 | 2
#3010 | 1 | 1 | 2
#3011 | 1 | 1 | 2
#3012 | 1 | 1 | 2
#3013 | 1 | 1 | 2
#3014 | 1 | 1 | 2
#3015 | 1 | 1 | 2
#3016 | 1 | 1 | 2
#3017 | 1 | 1 | 2
#3018 | 1 | 1 | 2
#3019 | 1 | 1 | 2
#3020 | 1 | 1 | 2
#3021 | 1 | 1 | 2
#3022 | 1 | 1 | 2
#3023 | 1 | 1 | 2
#3024 | 1 | 1 | 2
#3025 | 1 | 1 | 2
#3026 | 1 | 1 | 2
#3027 | 1 | 1 | 2
#3028 | 1 | 1 | 2
#3029 | 1 | 1 | 2
#3030 | 1 | 1 | 2
#3031 | 1 | 1 | 2
#3032 | 1 | 1 | 2
#3033 | 1 | 1 | 2
#3034 | 1 | 1 | 2
#3035 | 1 | 1 | 2
#3036 | 1 | 1 | 2
#3037 | 1 | 1 | 2
#3038 | 1 | 1 | 2
#39bb | 1 | 1 | 2
#4001 | 1 | 1 | 2
#4002 | 1 | 1 | 2
#4003 | 1 | 1 | 2
#4004 | 1 | 1 | 2
#4005 | 1 | 1 | 2
#5001 | 1 | 1 | 2
01004 | 1 | 1 | 2
01025 | 1 |  | 1
01032 |  | 1 | 1
05801 | 1 |  | 1
05806 | 1 | 1 | 2
06800 | 1 | 1 | 2
07000 | 1 | 1 | 2
10998 | 1 | 1 | 2
11100 | 1 | 1 | 2
11105 | 1 | 1 | 2
13491 | 1 | 1 | 2
13550 | 1 | 1 | 2
19099 | 1 | 1 | 2
19100 | 1 | 1 | 2
19110 | 1 | 1 | 2
19111 | 1 | 1 | 2
19112 | 1 | 1 | 2
19114 | 1 | 1 | 2
19128 | 1 | 1 | 2
19129 | 1 | 1 | 2
19130 | 1 | 1 | 2
19131 | 1 | 1 | 2
19132 | 1 | 1 | 2
19135 | 1 | 1 | 2
19138 | 1 | 1 | 2
20040 | 1 | 1 | 2
20050 | 1 | 1 | 2
20055 | 1 | 1 | 2
20057 | 1 |  | 1
20065 | 1 | 1 | 2
20066 | 1 | 1 | 2
20075 | 1 | 1 | 2
20100 | 1 | 1 | 2
20150 | 1 | 1 | 2
20160 | 1 | 1 | 2
20161 | 1 | 1 | 2
20171 | 1 | 1 | 2
20250 | 1 | 1 | 2
20260 | 1 | 1 | 2
20261 | 1 | 1 | 2
20700 | 1 | 1 | 2
20744 | 1 | 1 | 2
20745 | 1 | 1 | 2
20800 | 1 | 1 | 2
20805 | 1 | 1 | 2
20900 | 1 | 1 | 2
21000 | 1 | 1 | 2
21001 | 1 | 1 | 2
21009 | 1 | 1 | 2
21120 | 1 | 1 | 2
21121 | 1 | 1 | 2
21200 | 1 | 1 | 2
21410 | 1 | 1 | 2
21411 | 1 | 1 | 2
21550 | 1 | 1 | 2
21600 | 1 | 1 | 2
21640 | 1 | 1 | 2
21700 | 1 | 1 | 2
21809 | 1 | 1 | 2
21815 | 1 | 1 | 2
21950 | 1 | 1 | 2
22110 | 1 | 1 | 2
22355 | 1 | 1 | 2
22375 | 1 | 1 | 2
23300 | 1 | 1 | 2
23394 | 1 | 1 | 2
23397 | 1 | 1 | 2
23398 | 1 | 1 | 2
23400 | 1 | 1 | 2
23401 | 1 | 1 | 2
23402 | 1 | 1 | 2
23440 | 1 | 1 | 2
23455 | 1 | 1 | 2
23494 | 1 |  | 1
23499 | 1 | 1 | 2
23500 | 1 | 1 | 2
23501 | 1 | 1 | 2
23550 | 1 | 1 | 2
23600 | 1 | 1 | 2
23603 | 1 | 1 | 2
23608 | 1 | 1 | 2
23609 | 1 | 1 | 2
23615 | 1 | 1 | 2
23650 | 1 | 1 | 2
23700 | 1 | 1 | 2
23939 | 1 | 1 | 2
24000 | 1 | 1 | 2
24099 | 1 | 1 | 2
24100 | 1 | 1 | 2
24101 | 1 |  | 1
24103 | 1 | 1 | 2
24104 | 1 | 1 | 2
24209 | 1 | 1 | 2
24210 | 1 | 1 | 2
24410 | 1 | 1 | 2
24460 | 1 | 1 | 2
24500 | 1 | 1 | 2
24510 | 1 | 1 | 2
24550 | 1 | 1 | 2
24551 | 1 | 1 | 2
24552 | 1 | 1 | 2
24560 | 1 | 1 | 2
24570 | 1 | 1 | 2
24610 | 1 | 1 | 2
24611 | 1 | 1 | 2
27005 | 1 | 1 | 2
27007 | 1 | 1 | 2
27201 | 1 | 1 | 2
27400 | 1 | 1 | 2
30001 | 1 | 1 | 2
30100 | 1 | 1 | 2
30172 | 1 | 1 | 2
30173 | 1 | 1 | 2
30175 | 1 | 1 | 2
30180 | 1 | 1 | 2
30199 | 1 | 1 | 2
30200 | 1 | 1 | 2
30290 | 1 | 1 | 2
30300 | 1 | 1 | 2
30390 | 1 | 1 | 2
30460 | 1 | 1 | 2
30500 | 1 | 1 | 2
30510 | 1 | 1 | 2
30515 | 1 | 1 | 2
30530 | 1 | 1 | 2
30600 | 1 | 1 | 2
30650 | 1 | 1 | 2
30700 | 1 | 1 | 2
30850 | 1 | 1 | 2
30855 | 1 | 1 | 2
31000 | 1 | 1 | 2
31095 | 1 | 1 | 2
31100 | 1 | 1 | 2
31121 | 1 | 1 | 2
31150 | 1 | 1 | 2
31170 | 1 | 1 | 2
31175 | 1 | 1 | 2
31205 | 1 | 1 | 2
31210 | 1 | 1 | 2
31800 | 1 | 1 | 2
31805 | 1 | 1 | 2
31830 | 1 | 1 | 2
31831 | 1 | 1 | 2
31885 | 1 | 1 | 2
31900 | 1 | 1 | 2
31901 | 1 | 1 | 2
31904 | 1 | 1 | 2
31913 | 1 | 1 | 2
31919 | 1 | 1 | 2
31921 | 1 | 1 | 2
31924 | 1 | 1 | 2
31925 | 1 | 1 | 2
31926 | 1 | 1 | 2
31927 | 1 | 1 | 2
31933 | 1 | 1 | 2
31934 | 1 | 1 | 2
31936 | 1 | 1 | 2
31937 | 1 | 1 | 2
31950 | 1 | 1 | 2
32050 | 1 | 1 | 2
32100 | 1 | 1 | 2
32101 | 1 | 1 | 2
32130 | 1 | 1 | 2
32300 | 1 | 1 | 2
32400 | 1 | 1 | 2
32401 | 1 | 1 | 2
32600 | 1 | 1 | 2
32790 | 1 | 1 | 2
32800 | 1 | 1 | 2
32840 | 1 | 1 | 2
32842 | 1 | 1 | 2
32846 | 1 | 1 | 2
32847 | 1 | 1 | 2
32848 | 1 | 1 | 2
32849 | 1 | 1 | 2
32850 | 1 | 1 | 2
32851 | 1 | 1 | 2
32855 | 1 | 1 | 2
32875 | 1 | 1 | 2
32900 | 1 | 1 | 2
33220 | 1 | 1 | 2
33250 | 1 | 1 | 2
33256 | 1 | 1 | 2
33281 | 1 | 1 | 2
33300 | 1 | 1 | 2
33301 | 1 | 1 | 2
33310 | 1 | 1 | 2
33320 | 1 | 1 | 2
33321 | 1 | 1 | 2
33350 | 1 | 1 | 2
33356 | 1 | 1 | 2
33360 | 1 | 1 | 2
33400 | 1 | 1 | 2
33401 | 1 | 1 | 2
33430 | 1 | 1 | 2
33470 | 1 | 1 | 2
33475 | 1 | 1 | 2
33900 | 1 | 1 | 2
34200 | 1 | 1 | 2
34201 | 1 | 1 | 2
34330 | 1 | 1 | 2
34400 | 1 | 1 | 2
34401 | 1 |  | 1
34405 | 1 | 1 | 2
34410 | 1 | 1 | 2
34500 | 1 | 1 | 2
34549 | 1 | 1 | 2
34550 | 1 | 1 | 2
34600 | 1 | 1 | 2
34642 | 1 | 1 | 2
34651 | 1 | 1 | 2
34653 | 1 | 1 | 2
34654 | 1 |  | 1
34725 | 1 | 1 | 2
34745 | 1 | 1 | 2
34940 | 1 | 1 | 2
34965 | 1 | 1 | 2
34975 | 1 | 1 | 2
35360 | 1 | 1 | 2
35450 | 1 | 1 | 2
35451 | 1 | 1 | 2
35454 | 1 | 1 | 2
35650 | 1 | 1 | 2
35651 | 1 | 1 | 2
35653 | 1 | 1 | 2
35660 | 1 | 1 | 2
35665 | 1 | 1 | 2
35690 | 1 | 1 | 2
35700 | 1 | 1 | 2
35710 | 1 | 1 | 2
35711 | 1 | 1 | 2
35750 | 1 | 1 | 2
35790 | 1 | 1 | 2
35791 | 1 | 1 | 2
35797 | 1 | 1 | 2
35800 | 1 | 1 | 2
35810 | 1 | 1 | 2
35941 | 1 | 1 | 2
35950 | 1 | 1 | 2
35955 | 1 | 1 | 2
36000 | 1 | 1 | 2
36060 | 1 | 1 | 2
36190 | 1 | 1 | 2
36200 | 1 | 1 | 2
36210 | 1 | 1 | 2
36211 | 1 |  | 1
36220 | 1 | 1 | 2
36230 | 1 | 1 | 2
36290 | 1 | 1 | 2
36300 | 1 | 1 | 2
36400 | 1 | 1 | 2
36450 | 1 | 1 | 2
36452 | 1 | 1 | 2
36459 | 1 | 1 | 2
36700 | 1 | 1 | 2
36710 | 1 | 1 | 2
36850 | 1 | 1 | 2
37301 | 1 | 1 | 2
37400 | 1 | 1 | 2
37600 | 1 | 1 | 2
37800 | 1 | 1 | 2
37850 | 1 | 1 | 2
37896 | 1 | 1 | 2
37905 | 1 | 1 | 2
38100 | 1 | 1 | 2
38160 | 1 | 1 | 2
38200 | 1 | 1 | 2
38205 | 1 | 1 | 2
38230 | 1 | 1 | 2
38300 | 1 | 1 | 2
38400 | 1 | 1 | 2
38500 | 1 | 1 | 2
38501 | 1 | 1 | 2
38505 | 1 | 1 | 2
38550 | 1 | 1 | 2
38700 | 1 | 1 | 2
38702 | 1 | 1 | 2
38703 | 1 | 1 | 2
38900 | 1 | 1 | 2
39000 | 1 | 1 | 2
39100 | 1 | 1 | 2
39300 | 1 | 1 | 2
39301 | 1 | 1 | 2
39310 | 1 | 1 | 2
39400 | 1 | 1 | 2
39401 | 1 | 1 | 2
39800 | 1 | 1 | 2
39850 | 1 | 1 | 2
39900 | 1 | 1 | 2
39910 | 1 | 1 | 2
39998 | 1 | 1 | 2
39999 | 1 | 1 | 2
40000 | 1 | 1 | 2
40125 | 1 | 1 | 2
40150 | 1 | 1 | 2
40190 | 1 | 1 | 2
40195 | 1 | 1 | 2
40197 | 1 | 1 | 2
40200 | 1 | 1 | 2
40400 | 1 | 1 | 2
40600 | 1 | 1 | 2
40800 | 1 | 1 | 2
40900 | 1 | 1 | 2
40992 | 1 | 1 | 2
40993 | 1 | 1 | 2
41000 | 1 | 1 | 2
41011 | 1 | 1 | 2
41012 | 1 | 1 | 2
41020 | 1 | 1 | 2
41031 | 1 | 1 | 2
41040 | 1 | 1 | 2
41052 | 1 | 1 | 2
41055 | 1 | 1 | 2
41060 | 1 | 1 | 2
41061 | 1 | 1 | 2
41065 | 1 | 1 | 2
41100 | 1 | 1 | 2
41150 | 1 | 1 | 2
41160 | 1 | 1 | 2
41203 | 1 | 1 | 2
41205 | 1 | 1 | 2
41206 | 1 | 1 | 2
41208 | 1 | 1 | 2
41210 | 1 | 1 | 2
41250 | 1 | 1 | 2
41260 | 1 | 1 | 2
41300 | 1 | 1 | 2
41450 | 1 | 1 | 2
41500 | 1 | 1 | 2
41600 | 1 | 1 | 2
41750 | 1 | 1 | 2
41800 | 1 | 1 | 2
41837 | 1 | 1 | 2
41847 | 1 | 1 | 2
41855 | 1 | 1 | 2
41950 | 1 | 1 | 2
42000 | 1 | 1 | 2
42015 | 1 |  | 1
42100 | 1 | 1 | 2
42180 | 1 | 1 | 2
42181 | 1 | 1 | 2
42225 | 1 | 1 | 2
42226 | 1 | 1 | 2
42230 | 1 | 1 | 2
42300 | 1 | 1 | 2
43220 | 1 | 1 | 2
43325 | 1 | 1 | 2
49900 | 1 | 1 | 2
49901 | 1 | 1 | 2

## Sheet3
Count of ActivityID | Column Labels
Row Labels | Current | NEW | Grand Total
#1001 | 1 | 1 | 2
#1002 | 1 | 1 | 2
#1003 | 1 | 1 | 2
#1004 | 1 | 1 | 2
#1zbb | 1 | 1 | 2
#2s01 | 1 | 1 | 2
#2s02 | 1 | 1 | 2
#2s03 | 1 | 1 | 2
#2s04 | 1 | 1 | 2
#2s05 | 1 | 1 | 2
#2s06 | 1 | 1 | 2
#2s07 | 1 | 1 | 2
#2s08 | 1 |  | 1
#2s09 | 1 |  | 1
#2s10 | 1 |  | 1
#2zbb | 1 | 1 | 2
#3001 | 1 | 1 | 2
#3002 | 1 | 1 | 2
#3003 | 1 | 1 | 2
#3004 | 1 | 1 | 2
#3005 | 1 | 1 | 2
#3006 | 1 | 1 | 2
#3007 | 1 | 1 | 2
#3008 | 1 | 1 | 2
#3009 | 1 | 1 | 2
#3010 | 1 | 1 | 2
#3011 | 1 | 1 | 2
#3012 | 1 | 1 | 2
#3013 | 1 | 1 | 2
#3014 | 1 | 1 | 2
#3015 | 1 | 1 | 2
#3016 | 1 | 1 | 2
#3017 | 1 | 1 | 2
#3018 | 1 | 1 | 2
#3019 | 1 | 1 | 2
#3020 | 1 | 1 | 2
#3021 | 1 | 1 | 2
#3022 | 1 | 1 | 2
#3023 | 1 | 1 | 2
#3024 | 1 | 1 | 2
#3025 | 1 | 1 | 2
#3026 | 1 | 1 | 2
#3027 | 1 | 1 | 2
#3028 | 1 | 1 | 2
#3029 | 1 | 1 | 2
#3030 | 1 | 1 | 2
#3031 | 1 | 1 | 2
#3032 | 1 | 1 | 2
#3033 | 1 | 1 | 2
#3034 | 1 | 1 | 2
#3035 | 1 | 1 | 2
#3036 | 1 | 1 | 2
#3037 | 1 | 1 | 2
#3038 | 1 | 1 | 2
#39bb | 1 | 1 | 2
#4001 | 1 | 1 | 2
#4002 | 1 | 1 | 2
#4003 | 1 | 1 | 2
#4004 | 1 | 1 | 2
#4005 | 1 | 1 | 2
#5001 | 1 | 1 | 2
01004 | 1 | 1 | 2
01025 | 1 |  | 1
01032 |  | 1 | 1
05801 | 1 |  | 1
05806 | 1 | 1 | 2
06800 | 1 | 1 | 2
07000 | 1 | 1 | 2
10998 | 1 | 1 | 2
11100 | 1 | 1 | 2
11105 | 1 | 1 | 2
13491 | 1 | 1 | 2
13550 | 1 | 1 | 2
19099 | 1 | 1 | 2
19100 | 1 | 1 | 2
19110 | 1 | 1 | 2
19111 | 1 | 1 | 2
19112 | 1 | 1 | 2
19114 | 1 | 1 | 2
19128 | 1 | 1 | 2
19129 | 1 | 1 | 2
19130 | 1 | 1 | 2
19131 | 1 | 1 | 2
19132 | 1 | 1 | 2
19135 | 1 | 1 | 2
19138 | 1 | 1 | 2
20040 | 1 | 1 | 2
20050 | 1 | 1 | 2
20055 | 1 | 1 | 2
20057 | 1 |  | 1
20065 | 1 | 1 | 2
20066 | 1 | 1 | 2
20075 | 1 | 1 | 2
20100 | 1 | 1 | 2
20150 | 1 | 1 | 2
20160 | 1 | 1 | 2
20161 | 1 | 1 | 2
20171 | 1 | 1 | 2
20250 | 1 | 1 | 2
20260 | 1 | 1 | 2
20261 | 1 | 1 | 2
20700 | 1 | 1 | 2
20744 | 1 | 1 | 2
20745 | 1 | 1 | 2
20800 | 1 | 1 | 2
20805 | 1 | 1 | 2
20900 | 1 | 1 | 2
21000 | 1 | 1 | 2
21001 | 1 | 1 | 2
21009 | 1 | 1 | 2
21120 | 1 | 1 | 2
21121 | 1 | 1 | 2
21200 | 1 | 1 | 2
21410 | 1 | 1 | 2
21411 | 1 | 1 | 2
21550 | 1 | 1 | 2
21600 | 1 | 1 | 2
21640 | 1 | 1 | 2
21700 | 1 | 1 | 2
21809 | 1 | 1 | 2
21815 | 1 | 1 | 2
21950 | 1 | 1 | 2
22110 | 1 | 1 | 2
22355 | 1 | 1 | 2
22375 | 1 | 1 | 2
23300 | 1 | 1 | 2
23394 | 1 | 1 | 2
23397 | 1 | 1 | 2
23398 | 1 | 1 | 2
23400 | 1 | 1 | 2
23401 | 1 | 1 | 2
23402 | 1 | 1 | 2
23440 | 1 | 1 | 2
23455 | 1 | 1 | 2
23494 | 1 |  | 1
23499 | 1 | 1 | 2
23500 | 1 | 1 | 2
23501 | 1 | 1 | 2
23550 | 1 | 1 | 2
23600 | 1 | 1 | 2
23603 | 1 | 1 | 2
23608 | 1 | 1 | 2
23609 | 1 | 1 | 2
23615 | 1 | 1 | 2
23650 | 1 | 1 | 2
23700 | 1 | 1 | 2
23939 | 1 | 1 | 2
24000 | 1 | 1 | 2
24099 | 1 | 1 | 2
24100 | 1 | 1 | 2
24101 | 1 |  | 1
24103 | 1 | 1 | 2
24104 | 1 | 1 | 2
24209 | 1 | 1 | 2
24210 | 1 | 1 | 2
24410 | 1 | 1 | 2
24460 | 1 | 1 | 2
24500 | 1 | 1 | 2
24510 | 1 | 1 | 2
24550 | 1 | 1 | 2
24551 | 1 | 1 | 2
24552 | 1 | 1 | 2
24560 | 1 | 1 | 2
24570 | 1 | 1 | 2
24610 | 1 | 1 | 2
24611 | 1 | 1 | 2
27005 | 1 | 1 | 2
27007 | 1 | 1 | 2
27201 | 1 | 1 | 2
27400 | 1 | 1 | 2
30001 | 1 | 1 | 2
30100 | 1 | 1 | 2
30172 | 1 | 1 | 2
30173 | 1 | 1 | 2
30175 | 1 | 1 | 2
30180 | 1 | 1 | 2
30199 | 1 | 1 | 2
30200 | 1 | 1 | 2
30290 | 1 | 1 | 2
30300 | 1 | 1 | 2
30390 | 1 | 1 | 2
30460 | 1 | 1 | 2
30500 | 1 | 1 | 2
30510 | 1 | 1 | 2
30515 | 1 | 1 | 2
30530 | 1 | 1 | 2
30600 | 1 | 1 | 2
30650 | 1 | 1 | 2
30700 | 1 | 1 | 2
30850 | 1 | 1 | 2
30855 | 1 | 1 | 2
31000 | 1 | 1 | 2
31095 | 1 | 1 | 2
31100 | 1 | 1 | 2
31121 | 1 | 1 | 2
31150 | 1 | 1 | 2
31170 | 1 | 1 | 2
31175 | 1 | 1 | 2
31205 | 1 | 1 | 2
31210 | 1 | 1 | 2
31800 | 1 | 1 | 2
31805 | 1 | 1 | 2
31830 | 1 | 1 | 2
31831 | 1 | 1 | 2
31885 | 1 | 1 | 2
31900 | 1 | 1 | 2
31901 | 1 | 1 | 2
31904 | 1 | 1 | 2
31913 | 1 | 1 | 2
31919 | 1 | 1 | 2
31921 | 1 | 1 | 2
31924 | 1 | 1 | 2
31925 | 1 | 1 | 2
31926 | 1 | 1 | 2
31927 | 1 | 1 | 2
31933 | 1 | 1 | 2
31934 | 1 | 1 | 2
31936 | 1 | 1 | 2
31937 | 1 | 1 | 2
31950 | 1 | 1 | 2
32050 | 1 | 1 | 2
32100 | 1 | 1 | 2
32101 | 1 | 1 | 2
32130 | 1 | 1 | 2
32300 | 1 | 1 | 2
32400 | 1 | 1 | 2
32401 | 1 | 1 | 2
32600 | 1 | 1 | 2
32790 | 1 | 1 | 2
32800 | 1 | 1 | 2
32840 | 1 | 1 | 2
32842 | 1 | 1 | 2
32846 | 1 | 1 | 2
32847 | 1 | 1 | 2
32848 | 1 | 1 | 2
32849 | 1 | 1 | 2
32850 | 1 | 1 | 2
32851 | 1 | 1 | 2
32855 | 1 | 1 | 2
32875 | 1 | 1 | 2
32900 | 1 | 1 | 2
33220 | 1 | 1 | 2
33250 | 1 | 1 | 2
33256 | 1 | 1 | 2
33281 | 1 | 1 | 2
33300 | 1 | 1 | 2
33301 | 1 | 1 | 2
33310 | 1 | 1 | 2
33320 | 1 | 1 | 2
33321 | 1 | 1 | 2
33350 | 1 | 1 | 2
33356 | 1 | 1 | 2
33360 | 1 | 1 | 2
33400 | 1 | 1 | 2
33401 | 1 | 1 | 2
33430 | 1 | 1 | 2
33470 | 1 | 1 | 2
33475 | 1 | 1 | 2
33900 | 1 | 1 | 2
34200 | 1 | 1 | 2
34201 | 1 | 1 | 2
34330 | 1 | 1 | 2
34400 | 1 | 1 | 2
34401 | 1 |  | 1
34405 | 1 | 1 | 2
34410 | 1 | 1 | 2
34500 | 1 | 1 | 2
34549 | 1 | 1 | 2
34550 | 1 | 1 | 2
34600 | 1 | 1 | 2
34642 | 1 | 1 | 2
34651 | 1 | 1 | 2
34653 | 1 | 1 | 2
34654 | 1 |  | 1
34725 | 1 | 1 | 2
34745 | 1 | 1 | 2
34940 | 1 | 1 | 2
34965 | 1 | 1 | 2
34975 | 1 | 1 | 2
35360 | 1 | 1 | 2
35450 | 1 | 1 | 2
35451 | 1 | 1 | 2
35454 | 1 | 1 | 2
35650 | 1 | 1 | 2
35651 | 1 | 1 | 2
35653 | 1 | 1 | 2
35660 | 1 | 1 | 2
35665 | 1 | 1 | 2
35690 | 1 | 1 | 2
35700 | 1 | 1 | 2
35710 | 1 | 1 | 2
35711 | 1 | 1 | 2
35750 | 1 | 1 | 2
35790 | 1 | 1 | 2
35791 | 1 | 1 | 2
35797 | 1 | 1 | 2
35800 | 1 | 1 | 2
35810 | 1 | 1 | 2
35941 | 1 | 1 | 2
35950 | 1 | 1 | 2
35955 | 1 | 1 | 2
36000 | 1 | 1 | 2
36060 | 1 | 1 | 2
36190 | 1 | 1 | 2
36200 | 1 | 1 | 2
36210 | 1 | 1 | 2
36211 | 1 |  | 1
36220 | 1 | 1 | 2
36230 | 1 | 1 | 2
36290 | 1 | 1 | 2
36300 | 1 | 1 | 2
36400 | 1 | 1 | 2
36450 | 1 | 1 | 2
36452 | 1 | 1 | 2
36459 | 1 | 1 | 2
36700 | 1 | 1 | 2
36710 | 1 | 1 | 2
36850 | 1 | 1 | 2
37301 | 1 | 1 | 2
37400 | 1 | 1 | 2
37600 | 1 | 1 | 2
37800 | 1 | 1 | 2
37850 | 1 | 1 | 2
37896 | 1 | 1 | 2
37905 | 1 | 1 | 2
38100 | 1 | 1 | 2
38160 | 1 | 1 | 2
38200 | 1 | 1 | 2
38205 | 1 | 1 | 2
38230 | 1 | 1 | 2
38300 | 1 | 1 | 2
38400 | 1 | 1 | 2
38500 | 1 | 1 | 2
38501 | 1 | 1 | 2
38505 | 1 | 1 | 2
38550 | 1 | 1 | 2
38700 | 1 | 1 | 2
38702 | 1 | 1 | 2
38703 | 1 | 1 | 2
38900 | 1 | 1 | 2
39000 | 1 | 1 | 2
39100 | 1 | 1 | 2
39300 | 1 | 1 | 2
39301 | 1 | 1 | 2
39310 | 1 | 1 | 2
39400 | 1 | 1 | 2
39401 | 1 | 1 | 2
39800 | 1 | 1 | 2
39850 | 1 | 1 | 2
39900 | 1 | 1 | 2
39910 | 1 | 1 | 2
39998 | 1 | 1 | 2
39999 | 1 | 1 | 2
40000 | 1 | 1 | 2
40125 | 1 | 1 | 2
40150 | 1 | 1 | 2
40190 | 1 | 1 | 2
40195 | 1 | 1 | 2
40197 | 1 | 1 | 2
40200 | 1 | 1 | 2
40400 | 1 | 1 | 2
40600 | 1 | 1 | 2
40800 | 1 | 1 | 2
40900 | 1 | 1 | 2
40992 | 1 | 1 | 2
40993 | 1 | 1 | 2
41000 | 1 | 1 | 2
41011 | 1 | 1 | 2
41012 | 1 | 1 | 2
41020 | 1 | 1 | 2
41031 | 1 | 1 | 2
41040 | 1 | 1 | 2
41052 | 1 | 1 | 2
41055 | 1 | 1 | 2
41060 | 1 | 1 | 2
41061 | 1 | 1 | 2
41065 | 1 | 1 | 2
41100 | 1 | 1 | 2
41150 | 1 | 1 | 2
41160 | 1 | 1 | 2
41203 | 1 | 1 | 2
41205 | 1 | 1 | 2
41206 | 1 | 1 | 2
41208 | 1 | 1 | 2
41210 | 1 | 1 | 2
41250 | 1 | 1 | 2
41260 | 1 | 1 | 2
41300 | 1 | 1 | 2
41450 | 1 | 1 | 2
41500 | 1 | 1 | 2
41600 | 1 | 1 | 2
41750 | 1 | 1 | 2
41800 | 1 | 1 | 2
41837 | 1 | 1 | 2
41847 | 1 | 1 | 2
41855 | 1 | 1 | 2
41950 | 1 | 1 | 2
42000 | 1 | 1 | 2
42015 | 1 |  | 1
42100 | 1 | 1 | 2
42180 | 1 | 1 | 2
42181 | 1 | 1 | 2
42225 | 1 | 1 | 2
42226 | 1 | 1 | 2
42230 | 1 | 1 | 2
42300 | 1 | 1 | 2
43220 | 1 | 1 | 2
43325 | 1 | 1 | 2
49900 | 1 | 1 | 2
49901 | 1 | 1 | 2
Grand Total | 409 | 398 | 807

## Sheet2
XXXX | ActivityID | Activity Name
NEW | #1001 | _Pre_Construction_Day_01
NEW | 01032 | Atl Slab 09-2024 (Chatt)
NEW | 13491 | Impact Fee - Building
NEW | 13550 | CM - Inspect Pad
NEW | 19099 | Sewer Tap Fees Budget
NEW | 19100 | Sewer Tap Fees
NEW | 19110 | Water MeterFees (2ndary)
NEW | 19111 | Water Fees
NEW | 19112 | Water Fees Budget
NEW | 19114 | Water Deposit Fees
NEW | 19128 | Building Permit Budget
NEW | 19129 | Building Permits Budget
NEW | 19130 | Purchase BuildingPermits
NEW | 19131 | Purchase BuildingPermit
NEW | 19132 | Purch Electrical Permit
NEW | 19135 | Reinspection Fee
NEW | 19138 | Purch Elec Permit-Budget
NEW | 20040 | SURVEY - Order HLP-Sched
NEW | 20150 | CAD - Plans Complete
NEW | 20160 | DIV - Print House Plans
NEW | 20250 | Septic Permit Fees Budgt
NEW | 20260 | Purchase Septic Permits
NEW | 20261 | PurchaseSepticPermits PO
NEW | 21411 | Temporary Power - Budget
NEW | 21600 | Misc Engineering
NEW | 32400 | Gas Service Line
NEW | 32401 | Gas Service Line-Budget
NEW | 41208 | Electric Meter-Check
NEW | #1002 | _Pre_Construction_Day_02
NEW | 20050 | SURVEY - Delvr HLP
NEW | #1003 | _Pre_Construction_Day_03
NEW | 20055 | CM - Review/Approve HLP
NEW | 20075 | CM - Apply for PermPower
NEW | 20100 | DIV - Check/Enter LotAdj
NEW | 20161 | DIV - Send Starts Email
NEW | 20171 | EST - QAChk[EstApprONLY]
NEW | 20744 | CM - Sch Erosion Inspect
NEW | 20800 | CM - Inst Permit Board
NEW | 20900 | Install Temp Power Pole
NEW | 21000 | CM-Apply TempPower Metr
NEW | 21001 | TP Apply Temp Power Metr
NEW | 21009 | Deliver Trash Container
NEW | 21120 | CM - Sch Temp Power Insp
NEW | 21121 | TP Sch TempPower Inspect
NEW | 21550 | Install Silt Fence
NEW | #1004 | _Pre_Construction_Day_04
NEW | 22355 | PP Apply BuildingPermit
NEW | #1zbb | _FOUNDATION_BUFFER______
NEW | #2s01 | _Foundation_Slab_Day_01_
NEW | 20700 | Clear Lot Complete
NEW | 20745 | SITE INSPECTION(erosion)
NEW | 20805 | CM - Plans on Site
NEW | 21700 | SURVEY-Stake House Crnrs
NEW | 22375 | PP Municipality Permit
NEW | 23455 | Delr Slab/Basement Stone
NEW | 23615 | Delvr Slab Form Material
NEW | 21410 | Temporary Power
NEW | 21809 | Set Slab Forms(CFinish)
NEW | 21815 | CM - Insp/call box chk
NEW | 23440 | CM-CallForSlab/BsmtStone
NEW | 32875 | Install Piers
NEW | 38230 | Lot Retaining Wall
NEW | 39401 | Erosion Control-Budget
NEW | #2s02 | _Foundation_Slab_Day_02_
NEW | 22110 | CM - Insp Slab Plumbing
NEW | 23300 | Install Slab Plumbing
NEW | 23394 | CM - Sch Conduit Inspect
NEW | 23397 | Install Conduit-Island
NEW | 23398 | Install Conduit-Outlets
NEW | 23400 | CM - Sch Slab Plumb Insp
NEW | 23402 | TP Sch Slab Plumb Insp
NEW | 23499 | Run Sewer/Water Line-WSL
NEW | 23500 | Run Sewer/Water Line-Pl
NEW | 27201 | Found Survey Field Shots
NEW | #2s03 | _Foundation_Slab_Day_03_
NEW | 23401 | CM - Conduit Inspection
NEW | 23600 | SLAB PLUMBING INSP COMPL
NEW | 24099 | Slab PlumbInspSrvc-3p
NEW | #2s04 | _Foundation_Slab_Day_04_
NEW | 23700 | CM - Sch Slab Inspection
NEW | 23939 | Prep Slab(CFinish)
NEW | #2s05 | _Foundation_Slab_Day_05_
NEW | 21950 | SURVEY-Foundation Survey
NEW | 24000 | SLAB INSPECTION COMPL
NEW | 24100 | Slab Inspection Srvc-3p
NEW | 30290 | BDLR-Slab pic w/permit #
NEW | #2s06 | _Foundation_Slab_Day_06_
NEW | 05806 | Pour Garag/Porch/StepPad
NEW | 24410 | Deliver Slab Concrete
NEW | 24460 | Concrete Pump Slab
NEW | 24510 | Finish Back/Front Porch
NEW | 24550 | Pour/Finish Slab
NEW | 24551 | Pour/Finish Turndown
NEW | 24552 | E Pour/Finish Drive/Walk
NEW | 24560 | CM - Inspect Poured Slab
NEW | 24611 | E Del Drive/Walk Conc
NEW | 30001 | Strip SlabForms(CFinish)
NEW | #2s07 | _Foundation_Slab_Day_07_
NEW | 31904 | Dig trench-power conduit
NEW | 34600 | Rough Grade
NEW | #2zbb | _FRAMING_BUFFER_________
NEW | #3001 | _Frame_to_QA_Day_01_____
NEW | 27400 | SURVEY-Del FoundChk Draw
NEW | 30100 | Deliver Frame 1
NEW | 30172 | Deliver Frame 2
NEW | 30173 | Deliver Frame 3
NEW | 30175 | Deliver Sheathing
NEW | 30180 | Dlvr Manufactured Beams
NEW | 30300 | Del Floor Trusses
NEW | 33356 | Straw Lot for Erosion
NEW | 21200 | TEMPORARY POWER INSPECT
NEW | 23501 | Offset water meter
NEW | 24570 | Cut curb at driveway
NEW | 27005 | If RDP Lot - Shoot Pad
NEW | 30200 | Deliver Roof Trusses
NEW | 30460 | Framing Day 1
NEW | 33401 | Measure Deck
NEW | 33900 | Order Cabinets/Tops
NEW | #3002 | _Frame_to_QA_Day_02_____
NEW | 33430 | Dlvr lumber Cvrd Porch
NEW | #3003 | _Frame_to_QA_Day_03_____
NEW | 30850 | Deliver Prefab Stairs
NEW | #3004 | _Frame_to_QA_Day_04_____
NEW | 30390 | CM - Email Slab Survey
NEW | #3005 | _Frame_to_QA_Day_05_____
NEW | 33400 | Deck Complete
NEW | #3006 | _Frame_to_QA_Day_06_____
NEW | 27007 | CM-Send FFE for RDP Lots
NEW | 30500 | Framing Cmplt - Pre Insp
NEW | 30510 | CM - Sch Sheathing Insp
NEW | 30530 | Screw Sub Floor
NEW | #3007 | _Frame_to_QA_Day_07_____
NEW | 06800 | Roof Material- First Out
NEW | 07000 | Roof Labor
NEW | 21640 | Sheathing Inspection
NEW | 30515 | CM - Sheathing Inspect
NEW | 30600 | Deliver Windows-FirstOut
NEW | 30650 | Delvr Ext Doors-FirstOut
NEW | 30700 | CM - Frame Checklist
NEW | 31095 | Plumbing Material Rough
NEW | 33281 | Pre-Insulation
NEW | 33360 | Measure Cabinets
NEW | 36290 | Measure Laminate Tops
NEW | 33470 | Dlvr Siding Mtrl Porch
NEW | 34965 | Dlvr Ext Trim and Siding
NEW | #3008 | _Frame_to_QA_Day_08_____
NEW | 31000 | Install Fireplace
NEW | 31100 | Plumbing - Rough Complet
NEW | 31121 | TP Schd Rough Plumb Insp
NEW | 31205 | Set Exterior Doors
NEW | 31210 | Set Window Complete
NEW | 32846 | Install House Wrap
NEW | 32847 | CM - Sch HouseWrap Insp
NEW | 34642 | Grinder Pump Day 1
NEW | 32840 | Vinyl Siding Day 1
NEW | 32842 | Cement Siding Day 1
NEW | #3009 | _Frame_to_QA_Day_09_____
NEW | 23550 | House Gas Service Line
NEW | 31150 | ROUGH PLUMBING INSPECT
NEW | 31170 | Roof Labor-Punch-Pl.Boot
NEW | 31800 | HVAC Rough Completed
NEW | 32101 | TP Rough HVAC Inspection
NEW | 32848 | HOUSE WRAP INSPECTION
NEW | 32849 | CM - Elev inFrontWindow
NEW | 34651 | Grinder Pump Completed
NEW | 34653 | TP Sch 1stGrinderP InsST
NEW | #3010 | _Frame_to_QA_Day_10_____
NEW | 31805 | Install GasLine-GasLT-PO
NEW | 31831 | TP Sch Gas Line Inspect
NEW | 31900 | Electric Rough Complete
NEW | 31901 | Low Voltage Rough Compl
NEW | 31919 | CM - Sch Rough Inspects
NEW | 31921 | TP Schd Rough Elec Inspe
NEW | 31924 | TP Sch Power Trench Insp
NEW | 31925 | Security Prewire
NEW | 32300 | Framing Punch Out
NEW | 32900 | Exterior Clean - Frame
NEW | 33301 | AIP/Firecaulk/Airseal
NEW | 23603 | 1st GINDER PUMP INSPECT
NEW | 32850 | Vinyl Siding Complete
NEW | 32851 | Cement Siding Complete
NEW | 34975 | Wrap Columns
NEW | #3011 | _Frame_to_QA_Day_11_____
NEW | 20065 | CM - Apply for Gas Srvc
NEW | 20066 | TP Apply for Gas Service
NEW | 23650 | Order Underground Power
NEW | 30199 | Del Eave Material
NEW | 31926 | CM - Sch PermPower Insp
NEW | 31927 | CM - Order PermPower
NEW | 31933 | TP Sch Perm Power Insp
NEW | 31934 | TP Order Perm Power
NEW | 31950 | ROUGH ELECTRIC INSPECT
NEW | 32050 | Sweep House Rough
NEW | 32100 | ROUGH HVAC INSPECTION
NEW | 32130 | PERM POWER INSPECTION
NEW | 33220 | CM - Sch Framing Inspect
NEW | 33250 | FRAMING INSPECTION
NEW | 33256 | Framing Cmplt -Post Insp
NEW | 33350 | CM - Pre Drywall Inspect
NEW | #3012 | _Frame_to_QA_Day_12_____
NEW | 24103 | Frame InspectionSrvc-3p
NEW | 31175 | Drain Water f/WasteLines
NEW | 33300 | Batts and Baffle Install
NEW | 33310 | CM - Sch Insulation Insp
NEW | 33321 | INSULATION AFFIDAVIT
NEW | #3013 | _Frame_to_QA_Day_13_____
NEW | 31885 | Electrical Trench Dig
NEW | 33320 | INSULATION INSPECTION
NEW | 38703 | Measure Shwr Door-Prefab
NEW | 33475 | Covrd Porch Siding Compl
NEW | #3014 | _Frame_to_QA_Day_14_____
NEW | 32855 | CM - Siding Inspection
NEW | 34200 | Deliver Drywall Material
NEW | 34201 | Carry Drywall-MatTr
NEW | 39800 | Exterior Clean - Siding
NEW | #3015 | _Frame_to_QA_Day_15_____
NEW | 24104 | InsulationInspSrvc-3p
NEW | 34330 | Drywall Day 1
NEW | 35450 | Paint Exterior Day 1
NEW | #3016 | _Frame_to_QA_Day_16_____
NEW | 34405 | Remove Drywall Waste
NEW | #3017 | _Frame_to_QA_Day_17_____
NEW | #3018 | _Frame_to_QA_Day_18_____
NEW | 32600 | Deliver Brick
NEW | 35451 | Paint Exterior Complete
NEW | #3019 | _Frame_to_QA_Day_19_____
NEW | 32790 | Brick Labor Day 1
NEW | 35941 | Stack Stone Labor Day 1
NEW | #3020 | _Frame_to_QA_Day_20_____
NEW | #3021 | _Frame_to_QA_Day_21_____
NEW | 34400 | Drywall Completed
NEW | 35750 | Sweep House Paint
NEW | 49901 | CM-Confirm Closing Day 1
NEW | #3022 | _Frame_to_QA_Day_22_____
NEW | 35790 | Paint Interior - Prime
NEW | 36190 | Deliver Cabinets
NEW | 37896 | Final Grade Day 1
NEW | #3023 | _Frame_to_QA_Day_23_____
NEW | 35360 | Inst Fireplace Surround
NEW | 35650 | Deliver Interior Trim
NEW | 35665 | Install Drip Edge
NEW | 35710 | Install Elect Fireplace
NEW | 36200 | Install Cabinets Complet
NEW | 36300 | Install Laminate Tops
NEW | 41837 | Deliver Drip Edge
NEW | 41847 | Drip Edge Completed
NEW | #3024 | _Frame_to_QA_Day_24_____
NEW | 24209 | Deliver Iron Box-Matrl
NEW | 32800 | Brick Labor Completed
NEW | 34500 | Exterior Clean - Drywall
NEW | 35690 | Interior Trim Day 1
NEW | 35950 | Stack Stone Complete
NEW | 36210 | Measure Granite Tops
NEW | 36220 | Measure Marble Top
NEW | 36230 | Measure SolidSurfaceTops
NEW | 49900 | ¦¦CONFIRM_CLOSING_DATE¦¦
NEW | #3025 | _Frame_to_QA_Day_25_____
NEW | 34410 | Drywall Prime Point Up
NEW | 35700 | Interior Trim Completed
NEW | 35955 | Roof Labor-BrickCntrFlsh
NEW | 36850 | Install Gutters Day 1
NEW | #3026 | _Frame_to_QA_Day_26_____
NEW | 34725 | Set Drive/WalkForms(CFin
NEW | 35797 | Dwall PrimePointUp Sand
NEW | #3027 | _Frame_to_QA_Day_27_____
NEW | 34745 | Finish Drive/Walk Day 1
NEW | 35791 | Paint Interior Day 1
NEW | #3028 | _Frame_to_QA_Day_28_____
NEW | 34549 | Garage Door Day 1
NEW | 35800 | Paint Interior Complete
NEW | #3029 | _Frame_to_QA_Day_29_____
NEW | 36000 | Hang Shutters Day 1
NEW | 36400 | Install Marble Tops
NEW | 36450 | Install Granite Tops
NEW | 36452 | Install SolidSurfaceTops
NEW | #3030 | _Frame_to_QA_Day_30_____
NEW | 10998 | Cer.Tile Set Bath Day 1
NEW | 34550 | Install Garage Door
NEW | 39999 | Tile Floor Day 1
NEW | 41020 | Garage Door Openers
NEW | #3031 | _Frame_to_QA_Day_31_____
NEW | 11100 | Ceramic Tile Set - Bath
NEW | 11105 | Ceramic Tile Set-Kitchen
NEW | 24500 | Pour/Finish Drive/Walk
NEW | 24610 | Del Drive/Walk Concrete
NEW | 37850 | Install Gutters Complete
NEW | 40000 | PM - Tile Floor Complete
NEW | 40150 | Install Hardwood Floor
NEW | 40190 | PM Install Vinyl Floor
NEW | 40195 | Install Vinyl Plank Lvl1
NEW | 40197 | Install Vinyl Plank Lvl2
NEW | #3032 | _Frame_to_QA_Day_32_____
NEW | 24210 | Deliver Iron Box-Plumber
NEW | 36060 | Shutters Complete
NEW | 36700 | Plumbing - Trim Complete
NEW | 36710 | Camera Sewer Line
NEW | 37600 | HVAC Trim Complete
NEW | 38160 | Landscaping Day 1
NEW | 38400 | Deliver Light Fixtures
NEW | 38700 | Measure Mirrors
NEW | 38702 | Measure Shwr Door - Tile
NEW | 39301 | Grab Bar
NEW | 39998 | Lockout Day 1
NEW | 41203 | Set Gas Meter (sched)
NEW | 41205 | Set Gas Meter
NEW | 41210 | Set Electric Meter
NEW | #3033 | _Frame_to_QA_Day_33_____
NEW | 30855 | Upgr Stair Treads/Lndng
NEW | 35651 | Delvr Ext Door Hardware
NEW | 35653 | Ext Door Lockout Complet
NEW | 35711 | Inst Linear Electric FP
NEW | 35810 | Deliver Locks - Interior
NEW | 37400 | PLUMBING FINAL INSPECT
NEW | 38100 | Blown Attic Insul Complt
NEW | 38500 | Electric Trim Complete
NEW | 38501 | Low Voltage Trim Complet
NEW | 38505 | Install Smart Switches
NEW | 38550 | Security Trim Complete
NEW | 39900 | Clean Interior - Rough
NEW | 39910 | Sweep for Flooring
NEW | 41000 | Lockout Complete
NEW | 41031 | TP Schd Elect Final Insp
NEW | 41300 | Smart Home Options
NEW | 41011 | TP Sch 3rdGrinderP InsET
NEW | 41012 | TP Sch 3rdGrinderP InsPT
NEW | #3034 | _Frame_to_QA_Day_34_____
NEW | 40200 | Install Carpet
NEW | 40992 | Shoemold Delivered
NEW | 41040 | ELECTRIC FINAL INSPECT
NEW | 41450 | HVAC Startup
NEW | 31936 | TP Sch 2ndGrinderP InsET
NEW | 31937 | TP Sch 2ndGrinderP InsPT
NEW | 23609 | 3rd GINDER PUMP INSPECT
NEW | #3035 | _Frame_to_QA_Day_35_____
NEW | 31913 | Del Res Drainage Study
NEW | 35660 | Ext Rails Tky Complete
NEW | 37301 | TP Schd Plmbng Finl Insp
NEW | 37800 | HVAC FINAL INSPECTION
NEW | 37905 | Final Grading Comp
NEW | 38200 | Landscaping Completed
NEW | 38205 | Haul Off Heavy Debris
NEW | 39000 | Install Mirrors
NEW | 39100 | Wire Shelving Installed
NEW | 39300 | Bath Hardware
NEW | 39310 | Bath Hardware Installed
NEW | 39400 | Silt Fence Final
NEW | 40993 | Shoemold Installed
NEW | 41052 | Purchase Mailbox
NEW | 41150 | Install Mailbox Complete
NEW | 41500 | FP StartUp-Gas Dir Vent
NEW | 41600 | Exterior Clean - Final
NEW | 42181 | Deliver RDP Certificate
NEW | 23608 | 2nd GINDER PUMP INSPECT
NEW | #3036 | _Frame_to_QA_Day_36_____
NEW | 31830 | Duct Blast Test
NEW | 38300 | Jet Sewer Line
NEW | 39850 | Pressure Wash Complete
NEW | 40125 | Drywall Point Up-Trade
NEW | 40400 | Del&Install AppliancePkg
NEW | 40600 | Del&Install Washer/Dryer
NEW | 40800 | Del&Install Refrigerator
NEW | 41061 | FINAL SEWER/PLUMB INSP
NEW | 43325 | Blower Door Test
NEW | #3037 | _Frame_to_QA_Day_37_____
NEW | 36459 | Roof Final
NEW | 38900 | Install Shower Doors
NEW | 41060 | CM - Sch Bldg C.O./Final
NEW | 41250 | Paint Touch-Up
NEW | 41260 | Stain Handrails
NEW | #3038 | _Frame_to_QA_Day_38_____
NEW | 34940 | Fence Install Complete
NEW | 35454 | Paint Ext Vinyl Home
NEW | 40900 | Deliver Window Screens
NEW | 41055 | Final Insp-3p Day 1
NEW | 41065 | Final InspectionSrvc-3p
NEW | 41100 | BUILDING C.O./FINAL
NEW | 41160 | Termite Baited System
NEW | 41750 | Clean Interior - Final
NEW | 41800 | CM - Q.A. Inspection
NEW | 42180 | SURVEY Del Final Survey
NEW | 43220 | CM - Place color info
NEW | #39bb | _CLOSING_BUFFER(Pre-HO)
NEW | #4001 | _Homeowner_Accept_Day_1_
NEW | 42000 | CM - Q.A. Accept
NEW | 42230 | Deliver & Install Blinds
NEW | 42100 | HO Pre-close Orientation
NEW | #4002 | _Homeowner_Accept_Day_2_
NEW | 41206 | Cabinet Punch
NEW | #4003 | _Homeowner_Accept_Day_3_
NEW | 41855 | Homeowner DrywallTouchup
NEW | #4004 | _Homeowner_Accept_Day_4_
NEW | 42225 | HO Paint Touchup
NEW | 42226 | Cabinet Punch Completed
NEW | #4005 | _Homeowner_Accept_Day_5_
NEW | 41950 | Clean Interior - HO T/U
NEW | #5001 | _Closing_Day_1__________
NEW | 01004 | Atlanta Slab 10-2023
NEW | 42300 | Homeowner Accept Walk
Current | #1001 | _Pre_Construction_Day_01
Current | 01025 | Atl Slab 06-2024 (Chatt)
Current | 13491 | Impact Fee - Building
Current | 13550 | CM - Inspect Pad
Current | 19099 | Sewer Tap Fees Budget
Current | 19100 | Sewer Tap Fees
Current | 19110 | Water MeterFees (2ndary)
Current | 19111 | Water Fees
Current | 19112 | Water Fees Budget
Current | 19114 | Water Deposit Fees
Current | 19128 | Building Permit Budget
Current | 19129 | Building Permits Budget
Current | 19130 | Purchase BuildingPermits
Current | 19131 | Purchase BuildingPermit
Current | 19132 | Purch Electrical Permit
Current | 19135 | Reinspection Fee
Current | 19138 | Purch Elec Permit-Budget
Current | 20040 | SURVEY - Order HLP-Sched
Current | 20150 | CAD - Plans Complete
Current | 20160 | DIV - Print House Plans
Current | 20250 | Septic Permit Fees Budgt
Current | 20260 | Purchase Septic Permits
Current | 20261 | PurchaseSepticPermits PO
Current | 21411 | Temporary Power - Budget
Current | 21600 | Misc Engineering
Current | 32400 | Gas Service Line
Current | 32401 | Gas Service Line-Budget
Current | 34654 | Grinder Pump Budget
Current | 41208 | Electric Meter-Check
Current | 42015 | Dumpster
Current | #1002 | _Pre_Construction_Day_02
Current | 20050 | SURVEY - Delvr HLP
Current | #1003 | _Pre_Construction_Day_03
Current | 20055 | CM - Review/Approve HLP
Current | 20075 | CM - Apply for PermPower
Current | 20100 | DIV - Check/Enter LotAdj
Current | 20161 | DIV - Send Starts Email
Current | 20171 | EST - QAChk[EstApprONLY]
Current | 20744 | CM - Sch Erosion Inspect
Current | 20800 | CM - Inst Permit Board
Current | 20900 | Install Temp Power Pole
Current | 21000 | CM-Apply TempPower Metr
Current | 21001 | TP Apply Temp Power Metr
Current | 21009 | Deliver Trash Container
Current | 21120 | CM - Sch Temp Power Insp
Current | 21121 | TP Sch TempPower Inspect
Current | 21550 | Install Silt Fence
Current | #1004 | _Pre_Construction_Day_04
Current | 22355 | PP Apply BuildingPermit
Current | #1zbb | _FOUNDATION_BUFFER______
Current | 20700 | Clear Lot Complete
Current | 20745 | SITE INSPECTION(erosion)
Current | 20805 | CM - Plans on Site
Current | 21700 | SURVEY-Stake House Crnrs
Current | 22375 | PP Municipality Permit
Current | 23455 | Delr Slab/Basement Stone
Current | 23615 | Delvr Slab Form Material
Current | #2s01 | _Foundation_Slab_Day_01_
Current | 20057 | T-Pole InspectService-3p
Current | 21410 | Temporary Power
Current | 21809 | Set Slab Forms(CFinish)
Current | 21815 | CM - Insp/call box chk
Current | 23440 | CM-CallForSlab/BsmtStone
Current | 23494 | Deliver Utility Rock
Current | 32875 | Install Piers
Current | 38230 | Lot Retaining Wall
Current | 39401 | Erosion Control-Budget
Current | #2s02 | _Foundation_Slab_Day_02_
Current | 22110 | CM - Insp Slab Plumbing
Current | 23300 | Install Slab Plumbing
Current | 23394 | CM - Sch Conduit Inspect
Current | 23397 | Install Conduit-Island
Current | 23398 | Install Conduit-Outlets
Current | 23400 | CM - Sch Slab Plumb Insp
Current | 23402 | TP Sch Slab Plumb Insp
Current | 23499 | Run Sewer/Water Line-WSL
Current | 23500 | Run Sewer/Water Line-Pl
Current | 27201 | Found Survey Field Shots
Current | #2s03 | _Foundation_Slab_Day_03_
Current | 23401 | CM - Conduit Inspection
Current | 23600 | SLAB PLUMBING INSP COMPL
Current | 24099 | Slab PlumbInspSrvc-3p
Current | #2s04 | _Foundation_Slab_Day_04_
Current | 23700 | CM - Sch Slab Inspection
Current | 23939 | Prep Slab(CFinish)
Current | #2s05 | _Foundation_Slab_Day_05_
Current | 21950 | SURVEY-Foundation Survey
Current | 24000 | SLAB INSPECTION COMPL
Current | 24100 | Slab Inspection Srvc-3p
Current | 24101 | BsmtWalFootngInspSrvc-3p
Current | 30290 | CM-Slab pic w/permit #
Current | #2s06 | _Foundation_Slab_Day_06_
Current | 05801 | Turnkey SlabComplete
Current | 05806 | Pour Garag/Porch/StepPad
Current | 24410 | Deliver Slab Concrete
Current | 24460 | Concrete Pump Slab
Current | 24510 | Finish Back/Front Porch
Current | 24550 | Pour/Finish Slab
Current | 24551 | Pour/Finish Turndown
Current | 24552 | E Pour/Finish Drive/Walk
Current | 24560 | CM - Inspect Poured Slab
Current | 24611 | E Del Drive/Walk Conc
Current | 30001 | Strip SlabForms(CFinish)
Current | #2s07 | _Foundation_Slab_Day_07_
Current | 34642 | Grinder Pump Day 1
Current | #2s08 | _Foundation_Slab_Day_08_
Current | 34651 | Grinder Pump Completed
Current | 34653 | TP Sch 1stGrinderP InsST
Current | #2s09 | _Foundation_Slab_Day_09_
Current | 23603 | 1st GINDER PUMP INSPECT
Current | #2s10 | _Foundation_Slab_Day_10_
Current | 31904 | Dig trench-power conduit
Current | 34600 | Rough Grade
Current | #2zbb | _FRAMING_BUFFER_________
Current | 27400 | SURVEY-Del FoundChk Draw
Current | 30100 | Deliver Frame 1
Current | 30172 | Deliver Frame 2
Current | 30173 | Deliver Frame 3
Current | 30175 | Deliver Sheathing
Current | 30180 | Dlvr Manufactured Beams
Current | 30300 | Del Floor Trusses
Current | 33356 | Straw Lot for Erosion
Current | #3001 | _Frame_to_QA_Day_01_____
Current | 21200 | TEMPORARY POWER INSPECT
Current | 23501 | Offset water meter
Current | 24570 | Cut curb at driveway
Current | 27005 | If RDP Lot - Shoot Pad
Current | 30200 | Deliver Roof Trusses
Current | 30460 | Framing Day 1
Current | 33401 | Measure Deck
Current | 33900 | Order Cabinets/Tops
Current | #3002 | _Frame_to_QA_Day_02_____
Current | 33430 | Dlvr lumber Cvrd Porch
Current | #3003 | _Frame_to_QA_Day_03_____
Current | 30850 | Deliver Prefab Stairs
Current | #3004 | _Frame_to_QA_Day_04_____
Current | 30390 | CM - Email Slab Survey
Current | #3005 | _Frame_to_QA_Day_05_____
Current | 33400 | Deck Complete
Current | #3006 | _Frame_to_QA_Day_06_____
Current | 27007 | CM-Send FFE for RDP Lots
Current | 30500 | Framing Cmplt - Pre Insp
Current | 30510 | CM - Sch Sheathing Insp
Current | 30530 | Screw Sub Floor
Current | #3007 | _Frame_to_QA_Day_07_____
Current | 06800 | Roof Material- First Out
Current | 07000 | Roof Labor
Current | 21640 | Sheathing Inspection
Current | 30515 | CM - Sheathing Inspect
Current | 30600 | Deliver Windows-FirstOut
Current | 30650 | Delvr Ext Doors-FirstOut
Current | 30700 | CM - Frame Checklist
Current | 31095 | Plumbing Material Rough
Current | 33281 | Pre-Insulation
Current | 33360 | Measure Cabinets
Current | 36290 | Measure Laminate Tops
Current | #3008 | _Frame_to_QA_Day_08_____
Current | 31000 | Install Fireplace
Current | 31100 | Plumbing - Rough Complet
Current | 31121 | TP Schd Rough Plumb Insp
Current | 31205 | Set Exterior Doors
Current | 31210 | Set Window Complete
Current | 32846 | Install House Wrap
Current | 32847 | CM - Sch HouseWrap Insp
Current | #3009 | _Frame_to_QA_Day_09_____
Current | 23550 | House Gas Service Line
Current | 31150 | ROUGH PLUMBING INSPECT
Current | 31170 | Roof Labor-Punch-Pl.Boot
Current | 31800 | HVAC Rough Completed
Current | 32101 | TP Rough HVAC Inspection
Current | 32848 | HOUSE WRAP INSPECTION
Current | 32849 | CM - Elev inFrontWindow
Current | #3010 | _Frame_to_QA_Day_10_____
Current | 31805 | Install GasLine-GasLT-PO
Current | 31831 | TP Sch Gas Line Inspect
Current | 31900 | Electric Rough Complete
Current | 31901 | Low Voltage Rough Compl
Current | 31919 | CM - Sch Rough Inspects
Current | 31921 | TP Schd Rough Elec Inspe
Current | 31924 | TP Sch Power Trench Insp
Current | 31925 | Security Prewire
Current | 31936 | TP Sch 2ndGrinderP InsET
Current | 31937 | TP Sch 2ndGrinderP InsPT
Current | 32300 | Framing Punch Out
Current | 32900 | Exterior Clean - Frame
Current | 33301 | AIP/Firecaulk/Airseal
Current | #3011 | _Frame_to_QA_Day_11_____
Current | 20065 | CM - Apply for Gas Srvc
Current | 20066 | TP Apply for Gas Service
Current | 23608 | 2nd GINDER PUMP INSPECT
Current | 23650 | Order Underground Power
Current | 24103 | Frame InspectionSrvc-3p
Current | 30199 | Del Eave Material
Current | 31926 | CM - Sch PermPower Insp
Current | 31927 | CM - Order PermPower
Current | 31933 | TP Sch Perm Power Insp
Current | 31934 | TP Order Perm Power
Current | 31950 | ROUGH ELECTRIC INSPECT
Current | 32050 | Sweep House Rough
Current | 32100 | ROUGH HVAC INSPECTION
Current | 32130 | PERM POWER INSPECTION
Current | 33220 | CM - Sch Framing Inspect
Current | 33250 | FRAMING INSPECTION
Current | 33256 | Framing Cmplt -Post Insp
Current | 33350 | CM - Pre Drywall Inspect
Current | 33470 | Dlvr Siding Mtrl Porch
Current | 34965 | Dlvr Ext Trim and Siding
Current | #3012 | _Frame_to_QA_Day_12_____
Current | 31175 | Drain Water f/WasteLines
Current | 32840 | Vinyl Siding Day 1
Current | 32842 | Cement Siding Day 1
Current | 33300 | Batts and Baffle Install
Current | 33310 | CM - Sch Insulation Insp
Current | 33321 | INSULATION AFFIDAVIT
Current | #3013 | _Frame_to_QA_Day_13_____
Current | 24104 | InsulationInspSrvc-3p
Current | 31885 | Electrical Trench Dig
Current | 33320 | INSULATION INSPECTION
Current | 38703 | Measure Shwr Door-Prefab
Current | #3014 | _Frame_to_QA_Day_14_____
Current | 32850 | Vinyl Siding Complete
Current | 32851 | Cement Siding Complete
Current | 32855 | CM - Siding Inspection
Current | 33475 | Covrd Porch Siding Compl
Current | 34200 | Deliver Drywall Material
Current | 34201 | Carry Drywall-MatTr
Current | 34401 | Carry Drywall-2nd-LabTr
Current | 34975 | Wrap Columns
Current | 39800 | Exterior Clean - Siding
Current | #3015 | _Frame_to_QA_Day_15_____
Current | 34330 | Drywall Day 1
Current | 35450 | Paint Exterior Day 1
Current | #3016 | _Frame_to_QA_Day_16_____
Current | 34405 | Remove Drywall Waste
Current | #3017 | _Frame_to_QA_Day_17_____
Current | #3018 | _Frame_to_QA_Day_18_____
Current | 32600 | Deliver Brick
Current | 35451 | Paint Exterior Complete
Current | 36211 | CM - Measure Tops
Current | #3019 | _Frame_to_QA_Day_19_____
Current | 32790 | Brick Labor Day 1
Current | 35941 | Stack Stone Labor Day 1
Current | #3020 | _Frame_to_QA_Day_20_____
Current | #3021 | _Frame_to_QA_Day_21_____
Current | 34400 | Drywall Completed
Current | 35750 | Sweep House Paint
Current | 49901 | CM-Confirm Closing Day 1
Current | #3022 | _Frame_to_QA_Day_22_____
Current | 35790 | Paint Interior - Prime
Current | 36190 | Deliver Cabinets
Current | 37896 | Final Grade Day 1
Current | #3023 | _Frame_to_QA_Day_23_____
Current | 35360 | Inst Fireplace Surround
Current | 35650 | Deliver Interior Trim
Current | 35665 | Install Drip Edge
Current | 35710 | Install Elect Fireplace
Current | 36200 | Install Cabinets Complet
Current | 36300 | Install Laminate Tops
Current | 41837 | Deliver Drip Edge
Current | 41847 | Drip Edge Completed
Current | #3024 | _Frame_to_QA_Day_24_____
Current | 24209 | Deliver Iron Box-Matrl
Current | 32800 | Brick Labor Completed
Current | 34500 | Exterior Clean - Drywall
Current | 35690 | Interior Trim Day 1
Current | 35950 | Stack Stone Complete
Current | 36210 | Measure Granite Tops
Current | 36220 | Measure Marble Top
Current | 36230 | Measure SolidSurfaceTops
Current | 49900 | ¦¦CONFIRM_CLOSING_DATE¦¦
Current | #3025 | _Frame_to_QA_Day_25_____
Current | 34410 | Drywall Prime Point Up
Current | 35700 | Interior Trim Completed
Current | 35955 | Roof Labor-BrickCntrFlsh
Current | 36850 | Install Gutters Day 1
Current | #3026 | _Frame_to_QA_Day_26_____
Current | 34725 | Set Drive/WalkForms(CFin
Current | 35797 | Dwall PrimePointUp Sand
Current | #3027 | _Frame_to_QA_Day_27_____
Current | 34745 | Finish Drive/Walk Day 1
Current | 35791 | Paint Interior Day 1
Current | #3028 | _Frame_to_QA_Day_28_____
Current | 34549 | Garage Door Day 1
Current | 35800 | Paint Interior Complete
Current | #3029 | _Frame_to_QA_Day_29_____
Current | 36000 | Hang Shutters Day 1
Current | 36400 | Install Marble Tops
Current | 36450 | Install Granite Tops
Current | 36452 | Install SolidSurfaceTops
Current | #3030 | _Frame_to_QA_Day_30_____
Current | 10998 | Cer.Tile Set Bath Day 1
Current | 34550 | Install Garage Door
Current | 39999 | Tile Floor Day 1
Current | 41020 | Garage Door Openers
Current | #3031 | _Frame_to_QA_Day_31_____
Current | 11100 | Ceramic Tile Set - Bath
Current | 11105 | Ceramic Tile Set-Kitchen
Current | 24500 | Pour/Finish Drive/Walk
Current | 24610 | Del Drive/Walk Concrete
Current | 37850 | Install Gutters Complete
Current | 40000 | PM - Tile Floor Complete
Current | 40150 | Install Hardwood Floor
Current | 40190 | PM Inst SheetVinyl Floor
Current | 40195 | Install Vinyl Plank Lvl1
Current | 40197 | Install Vinyl Plank Lvl2
Current | #3032 | _Frame_to_QA_Day_32_____
Current | 24210 | Deliver Iron Box-Plumber
Current | 36060 | Shutters Complete
Current | 36700 | Plumbing - Trim Complete
Current | 36710 | Camera Sewer Line
Current | 37600 | HVAC Trim Complete
Current | 38160 | Landscaping Day 1
Current | 38400 | Deliver Light Fixtures
Current | 38700 | Measure Mirrors
Current | 38702 | Measure Shwr Door - Tile
Current | 39301 | Grab Bar
Current | 39998 | Lockout Day 1
Current | 41203 | Set Gas Meter (sched)
Current | 41205 | Set Gas Meter
Current | 41210 | Set Electric Meter
Current | #3033 | _Frame_to_QA_Day_33_____
Current | 30855 | Upgr Stair Treads/Lndng
Current | 35651 | Delvr Ext Door Hardware
Current | 35653 | Ext Door Lockout Complet
Current | 35711 | Inst Linear Electric FP
Current | 35810 | Deliver Locks - Interior
Current | 37400 | PLUMBING FINAL INSPECT
Current | 38100 | Blown Attic Insul Complt
Current | 38500 | Electric Trim Complete
Current | 38501 | Low Voltage Trim Complet
Current | 38505 | Install Smart Switches
Current | 38550 | Security Trim Complete
Current | 39900 | Clean Interior - Rough
Current | 39910 | Sweep for Flooring
Current | 41000 | Lockout Complete
Current | 41011 | TP Sch 3rdGrinderP InsET
Current | 41012 | TP Sch 3rdGrinderP InsPT
Current | 41031 | TP Schd Elect Final Insp
Current | 41300 | Smart Home Options
Current | #3034 | _Frame_to_QA_Day_34_____
Current | 23609 | 3rd GINDER PUMP INSPECT
Current | 40200 | Install Carpet
Current | 40992 | Shoemold Delivered
Current | 41040 | ELECTRIC FINAL INSPECT
Current | 41450 | HVAC Startup
Current | #3035 | _Frame_to_QA_Day_35_____
Current | 31913 | Del Res Drainage Study
Current | 35660 | Ext Rails Tky Complete
Current | 37301 | TP Schd Plmbng Finl Insp
Current | 37800 | HVAC FINAL INSPECTION
Current | 37905 | Final Grading Comp
Current | 38200 | Landscaping Completed
Current | 38205 | Haul Off Heavy Debris
Current | 39000 | Install Mirrors
Current | 39100 | Wire Shelving Installed
Current | 39300 | Bath Hardware
Current | 39310 | Bath Hardware Installed
Current | 39400 | Silt Fence Final
Current | 40993 | Shoemold Installed
Current | 41052 | Purchase Mailbox
Current | 41150 | Install Mailbox Complete
Current | 41500 | FP StartUp-Gas Dir Vent
Current | 41600 | Exterior Clean - Final
Current | 42181 | Deliver RDP Certificate
Current | #3036 | _Frame_to_QA_Day_36_____
Current | 31830 | Duct Blast Test
Current | 38300 | Jet Sewer Line
Current | 39850 | Pressure Wash Complete
Current | 40125 | Drywall Point Up-Trade
Current | 40400 | Del&Install AppliancePkg
Current | 40600 | Del&Install Washer/Dryer
Current | 40800 | Del&Install Refrigerator
Current | 41061 | FINAL SEWER/PLUMB INSP
Current | 43325 | Blower Door Test
Current | #3037 | _Frame_to_QA_Day_37_____
Current | 36459 | Roof Final
Current | 38900 | Install Shower Doors
Current | 41060 | CM - Sch Bldg C.O./Final
Current | 41250 | Paint Touch-Up
Current | 41260 | Stain Handrails
Current | #3038 | _Frame_to_QA_Day_38_____
Current | 34940 | Fence Install Complete
Current | 35454 | Paint Ext Vinyl Home
Current | 40900 | Deliver Window Screens
Current | 41055 | Final Insp-3p Day 1
Current | 41065 | Final InspectionSrvc-3p
Current | 41100 | BUILDING C.O./FINAL
Current | 41160 | Termite Baited System
Current | 41750 | Clean Interior - Final
Current | 41800 | CM - Q.A. Inspection
Current | 42180 | SURVEY Del Final Survey
Current | 43220 | CM - Place color info
Current | #39bb | _CLOSING_BUFFER(Pre-HO)
Current | 42000 | CM - Q.A. Accept
Current | 42230 | Deliver & Install Blinds
Current | #4001 | _Homeowner_Accept_Day_1_
Current | 42100 | HO Pre-close Orientation
Current | #4002 | _Homeowner_Accept_Day_2_
Current | 41206 | Cabinet Punch
Current | #4003 | _Homeowner_Accept_Day_3_
Current | 41855 | Homeowner DrywallTouchup
Current | #4004 | _Homeowner_Accept_Day_4_
Current | 42225 | HO Paint Touchup
Current | 42226 | Cabinet Punch Completed
Current | #4005 | _Homeowner_Accept_Day_5_
Current | 41950 | Clean Interior - HO T/U
Current | #5001 | _Closing_Day_1__________
Current | 01004 | Atlanta Slab 10-2023
Current | 42300 | Homeowner Accept Walk

## Sheet1
#1001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
00020 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20111 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20119 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
01032 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
13491 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
13550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19099 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19110 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19111 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19112 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19114 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19128 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19129 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19130 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19131 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19132 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19135 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
19138 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20040 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20160 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20250 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20260 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20261 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21411 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32401 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41208 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#1002 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20050 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#1003 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20055 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20075 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20161 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20171 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20744 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21009 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21121 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#1004 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
22355 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#1zbb | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s01 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20745 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20805 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
22375 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23455 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23615 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21410 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21809 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21815 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23440 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32875 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38230 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39401 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s02 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
22110 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23394 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23397 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23398 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23402 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23499 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
27201 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s03 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23401 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24099 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s04 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23939 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s05 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21950 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30290 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s06 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
05806 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24410 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24460 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24510 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24551 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24552 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24560 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24611 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
05900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2s07 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31904 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#2zbb | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
27400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30172 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30173 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30175 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30180 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33356 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23501 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24570 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
27005 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30460 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33401 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3002 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33430 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3003 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30850 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3004 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30390 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3005 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3006 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
27007 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30510 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30530 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23494 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3007 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
06800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
07000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
21640 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30515 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30650 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31095 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33281 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33360 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36290 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33470 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34965 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3008 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31121 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31205 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31210 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32846 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32847 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34642 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32840 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32842 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3009 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31170 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32101 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32848 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32849 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34651 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34653 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3010 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31805 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31831 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31901 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31919 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31921 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31924 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31925 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33301 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23603 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32850 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32851 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34975 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3011 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20065 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
20066 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23650 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30199 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31926 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31927 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31933 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31934 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31950 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32050 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32130 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33220 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33250 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33256 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33350 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3012 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24103 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31175 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33310 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33321 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3013 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31885 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33320 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38703 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
33475 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3014 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32855 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34201 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34401 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3015 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24104 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34330 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35450 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3016 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34405 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3017 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3018 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35451 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3019 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32790 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35941 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3020 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3021 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35750 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
49901 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3022 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35790 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36190 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37896 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3023 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35360 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35650 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35665 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35710 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41837 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41847 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3024 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24209 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
32800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35690 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35950 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36210 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36220 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36230 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
49900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3025 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34410 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35955 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36850 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3026 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34725 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35797 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3027 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34745 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35791 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3028 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34549 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3029 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36450 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36452 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3030 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
10998 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39999 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41020 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3031 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
11100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
11105 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24610 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37850 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40190 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40195 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40197 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
05901 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3032 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
24210 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36060 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36710 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38160 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38702 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39301 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39998 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41203 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41205 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41210 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3033 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
30855 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35651 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35653 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35711 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35810 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38501 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38505 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39910 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41031 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41011 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41012 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3034 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40992 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41040 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41450 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31936 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31937 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23609 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3035 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31913 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35660 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37301 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
37905 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38205 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39310 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40993 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41052 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42181 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
23608 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3036 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
31830 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
39850 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40125 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41061 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
43325 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
36459 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
38900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41060 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41250 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41260 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#3038 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
34940 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
35454 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
40900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41055 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41065 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41160 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41750 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42180 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
43220 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#39bb | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#4001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42230 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#4002 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41206 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#4003 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41855 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#4004 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42225 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42226 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#4005 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
41950 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
#5001 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
01004 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
42300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL